## Sheet1
# | Item | Issue | Change | Justification | Status | Owner
1 | Model 2 event study plot | nb07 ran the event study on the full nationwide sample (1,000+ pairs), so the dynamic effects plot was not specific to the 4 illustrative borders highlighted in the report, leaving the parallel trends assumption untested for the pairs the visual narrative is actually built around. | Added a 4-line filter to nb07 Section 1 restricting the sample to the 4 illustrative border pairs (NJ-PA, MN-WI, NY-PA, CA-NV) Updated section 9 findings and notes accordingly | The nationwide event study aggregates across 1,000+ pairs and doesn't validate parallel trends for the specific borders used in the illustrative story. Restricting to the 4 selected borders confirms the parallel trends assumption holds precisely where the report's visual narrative is grounded. | TRUE | Tony
2 | Industry heterogeneity table | nb06 contains no cross-industry comparison of the main DiD estimate — the report references Figure 1 (elasticity plot across NAICS 722, 72, 44-45, 721) but there is no code that systematically runs the Model 1 spec across all four industries and outputs a compact results table. | Add a single cell at the end of Section 4 in nb06 that extracts p-values from a second pass through absorbed_ols and prints a clean β / SE / p-value table. Added table B2 + interpretation to appendix b of report | The teammate explicitly asked for a compact cross-industry comparison table. The β and SE are already computed — p-values just weren't collected in the original loop. | TRUE | Tony
6 | Appendix D — individual roles | Table is completely blank | Filled individual roles for the report | n/a | TRUE | All
7 | SE clustering inconsistency | The methods section in the report states standard errors are clustered at the state level, but nb06 and nb07 both cluster at the pair level throughout. These are inconsistent and one of them is wrong. | Updated the methods section in the report. | - | TRUE | Tony
8 | Callaway–Sant'Anna estimator | Report cites staggered treatment as limitation — implement CS and compare to TWFE | Added a new notebook 11_callaway_santanna.ipynb implementing the CS estimator on the nationwide NAICS 722 sample and outputting an aggregate ATT with confidence interval Added a comparison table to Appendix B showing the TWFE estimate (β = −0.027) alongside the CS aggregate ATT Updated the Limitations section to replace the staggered treatment paragraph with a note that the CS estimator was implemented as a robustness check and results are reported in Appendix B | 64% of pairs have their event year in 2010, making the TWFE estimate vulnerable to bias from heterogeneous treatment effects across adoption cohorts. Implementing CS directly converts a stated limitation into a finding — either it validates the TWFE null result, which strengthens the paper, or it reveals meaningful bias, which is itself an important result. Either way the paper is stronger for having done it. | FALSE | Oge
9 | Continuous treatment (mw_gap) | Dollar gap as treatment intensity instead of binary — ~20 lines, already in panel |  |  | FALSE | Mingjie
10 | Hours adjustment channel | UHRSWORKT in nb08 — construct hours-worked for 20–24 cohort, test vs headcount |  |  | FALSE | Mingjie
11 | Pre-2010 data Pre-2010 data zeros in figures | QCEW goes back to 1990 — get data or explicitly justify the 2010 start Figure 2 and several other figures show zeros for pre-2010 observations rather than actual data, because the dataset currently starts at 2010. These zeros are misleading and distort the visual pre-trend. |  | Either pull QCEW data back to 2004–2009 to populate the pre-period, or explicitly drop pre-2010 x-axis range from affected figures so no zero points are rendered. | FALSE | Tony
12 | Small-state CPS robustness | Drop states below n threshold, re-run age/gender estimates |  |  | FALSE | Mingjie
13 | SUTVA limitation — cross-border spillovers | Nick flagged that county-pair proximity introduces potential SUTVA violations: workers may cross the border to take jobs in higher-MW counties, and businesses in lower-MW counties may be forced to raise wages anyway. This biases estimates toward zero. |  | Add a paragraph to the Limitations section noting that county-pair proximity is a strength (shared economic conditions) and a weakness (spillover contamination). Frame estimates as a lower bound on true effects. | FALSE | Mingjie
14 | Figure 2 — add uncertainty + redo as event study | Nick noted Figure 2 communicates little about uncertainty and that a calendar-year x-axis is hard to interpret with staggered adoption. He suggested a staggered DiD event study plot with time-since-adoption on the x-axis instead. |  | Staggered event study plot (time since adoption) is the standard visualization for parallel trends under staggered treatment. Already partially in nb07 — needs uncertainty bands and axis fix. | FALSE
15 | Fix perfect-zero pre-trend coefficients in nb07 | Nick observed that the event study in nb07 returns perfect zeros for all pre-period coefficients, which is not realistic and signals a model setup error. |  | Perfect zeros indicate the reference period or dummies are mis-specified. Needs diagnosis and fix before the event study plot can be used as evidence of parallel trends. | FALSE | Tony
17 | Use causalpy for Figure 2 plot | Figure 2 is currently produced with raw matplotlib. Nick flagged it as the weak visualization in the memo — it lacks the standard event study aesthetics and uncertainty bands. |  | Replot Figure 2 using causalpy (PrePostFit or equivalent) to get built-in confidence bands and cleaner event study styling consistent with course conventions. | FALSE | Tony
18 | De-LLMification pass | Nick flagged uncertainty about how much of the memo was written by AI vs. the team. AI-written prose tends to be detectable and puts academic integrity at risk. |  | Each team member reads their sections and rewrites any passage they could not confidently explain or defend verbally. Remove hedging filler phrases and AI-typical sentence structures. | FALSE | All
19 | Citation audit — drop or verify unread papers | Some cited papers may have been added without being read in depth. Citing papers the team cannot explain is an academic integrity risk and weakens the literature review. |  | Each team member reviews every citation in their sections. Drop any paper not read in full or not understood well enough to summarize in one sentence. Replace with papers actually consulted. | FALSE | All